## Slide 1
TraceLM
UI Improvement Proposal
Modernize · Stabilize · Elevate
Version 1.0 | June 2026
Prepared for: TraceLM Development Team
TECHNICAL PROPOSAL

## Slide 2
OVERVIEW
What We Will Cover
Six focused topics from current state to implementation roadmap
01
Current State Assessment
Where TraceLM UI stands today
02
Identified Pain Points
Architecture and UX gaps
03
Phase 1 — Architecture
Decompose · Error Boundary · UI Toolkit
04
Phase 2 — User Experience
Progress · Preview · Empty States · Automation
05
Phase 3 — Productivity
Copy · Badges · Filter · Settings
06
Implementation Roadmap
Sequenced plan, effort, and quick wins
TraceLM | UI Improvement Proposal | Confidential

## Slide 3
CURRENT STATE
TraceLM UI Today
A functional but monolithic interface built for speed-to-market
1,036
Lines in App.tsx
Single React component
6
Tabs managed
All in one file
20+
useState hooks
Flat, co-mingled state
0
Error Boundaries
Full crash on any error
Key Pain Points Identified
Monolithic Architecture:
1,036-line App.tsx handles six tabs, routing, state, and all business logic — high maintenance burden
No Error Boundaries:
Any unhandled JS exception crashes the entire panel; no recovery without reopening the extension
Raw HTML Form Elements:
Custom CSS required for every VS Code theme; risk of visual drift on theme updates
Text-Only Progress:
Generate All shows '(2/4)...' string; no visual step status or in-progress indicator
Plain-Text Xray Preview:
Push preview is an unstyled list with Unicode symbols; no color, no actionable error hints
Low-Info Automation View:
Automation items render as pipe-delimited text; no title, no visual priority, no context
TraceLM | UI Improvement Proposal | Confidential

## Slide 4
PHASE 1 — ARCHITECTURE
Foundation First
Restructure before feature work — everything else becomes easier once this is in place
1.1
Decompose App.tsx
1.5 days
• SettingsTab.tsx
• RequirementsTab.tsx
• EnhancementTab.tsx
• ScenariosTab.tsx
• TestCasesTab.tsx
• AutomationTab.tsx
• useTraceLMMessages.ts hook
• App.tsx → tab router only
Pure structural split. Zero logic changes.
1.2
React Error Boundary
0.5 days
• Wrap each tab in ErrorBoundary
• Show fallback UI on tab crash
• Other tabs remain functional
• ~20 lines of new code total
Eliminates full-panel crash risk.
1.3
webview-ui-toolkit
1–2 days
• vscode-button replaces <button>
• vscode-text-field replaces <input>
• vscode-dropdown replaces <select>
• vscode-text-area replaces <textarea>
• vscode-checkbox replaces <input cb>
• Automatic theme inheritance
• No more custom CSS for forms
Light, dark, high-contrast — automatic.
TraceLM | UI Improvement Proposal | Confidential

## Slide 5
PHASE 2 — USER EXPERIENCE
High-Impact UX Improvements
Visible, user-facing changes that reduce confusion and improve daily workflow
2.1
Visual Step Progress
0.5 d effort
Replace '(2/4)...' text with a horizontal stepper showing Pending / In Progress / Completed state for all 4 generation steps.
2.2
Color-Coded Push Preview
0.5 d effort
Green = valid, Amber = duplicate, Red = validation error with inline fix hint. Replaces unstyled bullet list.
2.3
Collapsible Enhancement Cards
0.5 d effort
Add collapse/expand toggle to each of the 6 enhancement category cards. Users hide reviewed sections to reduce scroll.
2.4
Actionable Empty States
0.5 d effort
Replace 'No X generated yet.' plain text with structured blocks showing title + instruction + dependency tip.
2.5
Automation Candidate Cards
1.0 d effort
Replace pipe-delimited text lines with cards showing: title, priority badge (color-coded), ROI, Feasibility, exclusion reason.
TraceLM | UI Improvement Proposal | Confidential

## Slide 6
PHASE 3 — PRODUCTIVITY
Incremental Polish
Low-risk enhancements that improve power-user efficiency without structural changes
3.1
Copy-to-Clipboard Buttons
0.5 d effort
Copy icon on each Gherkin block and enhancement list item. Brief 'Copied!' confirmation. Eliminates select-all manual copy.
3.2
Tab Count Badges
0.5 d effort
Numeric badge on each tab button when data exists: 'Test Cases (12)'. At-a-glance status without switching tabs.
3.3
Test Case Layer Filter
0.5 d effort
Three chip toggles (Unit / API / UI) above the Structured Cases table. Multi-select, all layers shown by default.
3.4
Settings Visual Grouping
0.25 d effort
Visually separate 12 fields into: LLM Configuration · Jira Configuration · Xray Push Controls. CSS-only change.
TraceLM | UI Improvement Proposal | Confidential

## Slide 7
QUICK WINS
Start Here — Zero Dependencies
Three items deliverable immediately, before Phase 1 architecture work begins
⚡
Settings Visual Grouping
CSS-only change. Group 12 settings fields into three named sections with subtle background differentiation. No logic, no new components.
Impact: Immediate visual improvement visible on first launch after rebuild.
~30 min
Risk: Zero
📋
Actionable Empty States
Replace three plain 'No X yet.' paragraphs with structured empty-state blocks. Isolated paragraph-level changes, 10–15 lines per tab.
Impact: First-time users immediately see what to do next in each empty tab.
~1 hour
Risk: Very Low
🔴
Color-Coded Push Preview
Isolated to the xrayPushPreview render block in testCases tab. Replace <ul> with a styled table using CSS left-border colors per status.
Impact: Users see push readiness at a glance before committing the push action.
~2 hours
Risk: Low
TraceLM | UI Improvement Proposal | Confidential

## Slide 8
ROADMAP
Implementation Plan
Three phases sequenced for minimum risk and maximum incremental value
Phase 1
Architecture
3–4 days
✓ Decompose App.tsx
✓ React Error Boundary
✓ @vscode/webview-ui-toolkit
Phase 2
UX
2–3 days
✓ Step progress stepper
✓ Color-coded preview
✓ Collapsible cards
✓ Empty states
✓ Automation cards
Phase 3
Polish
1–2 days
✓ Copy buttons
✓ Tab badges
✓ Layer filter
✓ Settings groups
Total Estimated Effort: 6–9 developer days across all three phases
TraceLM | UI Improvement Proposal | Confidential

## Slide 9
RISK & DEPENDENCIES
What to Watch
All risks are low; mitigations are straightforward and already built into the plan
Risk
Likelihood
Impact
Mitigation
Phase 1 refactor introduces regression
Low
Medium
Pure structural split — no logic changes. Run typecheck + build after each file move.
webview-ui-toolkit visual differences
Low
Low
Toolkit inherits VS Code theme natively. Spot-check light and dark themes post-adoption.
Increased webview bundle size
Low
Low
Toolkit is tree-shakeable. Only imported components are bundled.
Phase 2/3 items without Phase 1 base
Medium
Low
Quick wins (3.4, 2.4, 2.2) can be done independently. All others follow Phase 1.
Package Dependency
Only one new npm package is required across all three phases:
@vscode/webview-ui-toolkit
Required for Phase 1.3 only. All other improvements use React and existing utilities — no additional packages.
Tree-shakeable: only imported components are bundled. Bundle size impact is negligible.
TraceLM | UI Improvement Proposal | Confidential

## Slide 10
SUCCESS METRICS
How We Measure Done
Objective, verifiable criteria for each phase of improvement
Metric
Current
Target
Phase
App.tsx line count
1,036 lines
< 200 lines
P1
Error Boundary coverage
0 boundaries
All 6 tabs wrapped
P1
Theme consistency
Manual CSS vars
Light / Dark / HC pass
P1
Generate All feedback
Text string only
Visual stepper active
P2
Push Preview clarity
Unicode symbols
Color-coded rows
P2
Empty state guidance
Plain text message
All 3 tabs with CTA
P2
Copy friction
Manual select-all
1-click copy on all blocks
P3
Tab data visibility
Must switch tab
Count badges on all tabs
P3
TraceLM | UI Improvement Proposal | Confidential

## Slide 11
Recommended Next Steps
01
Start Quick Wins Today
Settings grouping, empty states, push preview colors — all before any architecture work. Immediate visual improvement.
02
Plan Phase 1 Sprint
Allocate a focused 4-day sprint for App.tsx decomposition, Error Boundaries, and webview-ui-toolkit adoption.
03
Phase 2 + 3 in Following Sprint
Layer the UX and polish improvements on the stable Phase 1 foundation. Estimate 3–5 days combined.
TraceLM | UI Improvement Proposal | Version 1.0 | June 2026